## Estimate
Yoga & Egg Timer — iOS App Store release: effort & cost
Blue numbers are estimates you can change; totals recalculate.
Part | Low (h) | High (h) | Notes
Apple Developer enrollment, Xcode & signing setup | 2 | 4 | Plus Apple verification wait (days to ~2 weeks). Enroll as Texit Services LLC with D-U-N-S 136648910.
iOS cue scheduling (replaces Android foreground service) | 8 | 12 | Pre-schedule each cue as a local notification with the bowl sound; plays on the lock screen. Muted if the silent switch is on (vibration still works).
StoreKit purchase + free trial item | 6 | 10 | $2.99 non-consumable unlock + Restore; Apple-recommended $0 "Start 7-day trial" item.
TestFlight testing, listing, screenshots, review | 6 | 8 | iPhone-size screenshots, privacy labels ("no data collected"), existing privacy policy URL. Review usually 1–3 days.
Total | 22 | 34
Costs
Item | Amount (USD) | Frequency | Notes
Apple Developer Program | 99 | Per year | Organization enrollment (Texit Services LLC).
App Store Small Business Program | 0 | One-time signup | Free; reduces Apple commission from 30% to 15%.
Requires: your Mac with Xcode, and an iPhone for testing (simulator can't test locked-screen sounds).

## Scope
What carries over vs. what gets rebuilt
Area | iOS status | Notes
Timer screen, Settings, picker | Carries over | Shared web UI.
Trial logic | Carries over | Same 7-day trial; paired with a $0 trial item on iOS.
Sounds while app is open | Carries over | Web Audio.
Keep screen awake | Carries over | Capacitor plugin supports iOS.
Haptics / vibration | Carries over | Capacitor plugin supports iOS.
Saved settings | Carries over | Capacitor Preferences.
Locked-screen cues | Rebuild | iOS has no long-running timer service; schedule cues as local notifications.
Purchase | Rebuild | StoreKit replaces Google Play Billing.
Store listing & screenshots | New | iPhone sizes; App Store Connect.

## Checklist
Release checklist
Fill in the yellow Status and Done-on cells as you go. Status options: Not started / In progress / Waiting / Done.
# | Step | Status | Done on | Notes
1 | Enroll in Apple Developer Program as Texit Services LLC | In progress |  | Long wait — start first.
2 | Sign up for App Store Small Business Program | Not started |  | 15% commission.
3 | Add iOS platform: npx cap add ios; open in Xcode; set signing team | Not started
4 | Build iOS cue scheduling (local notifications + bowl sound) | Not started
5 | Build StoreKit unlock ($2.99) + $0 trial item + Restore | Not started
6 | Create app & products in App Store Connect | Not started
7 | TestFlight build; test on iPhone (locked screen, purchase, restore) | Not started
8 | Listing: iPhone screenshots, description, privacy labels, privacy URL | Not started
9 | Submit for App Review | Not started |  | Usually 1–3 days.
| Steps done | 0 of 9